## Old E-creds Estimates
S. No. | Macro Use Case | eCreds User Story | BE | Testing | If NA | Total | Status
1 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As an admin user, I should be able to register myself so that I can log-in. | 10 | 4 | 0 | 14
2 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As an admin user, I should be able to log-in so that I can use the application. | 15 | 4 | 0 | 19
3 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As an admin user, I should be able to view my Landing Page so that I can access features of the application. | NA | NA | 1 | NA | We have been requested to put a hold on FE
4 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As a workplace user, I should be able to register myself so that I can log-in. | 10 | 4 | 0 | 14
5 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As a workplace user, I should be able to log-in so that I can use the application. | 15 | 4 | 0 | 19
6 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As a workplace user, I should be able to view my Landing Page so that I can access features of the application. | NA | NA | 1 | NA | We have been requested to put a hold on FE
7 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As a candidate user, I should be able to register myself so that I can log-in. | 10 | 4 | 0 | 14
8 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As a candidate user, I should be able to log-in so that I can use the application. | 15 | 4 | 0 | 19
9 | UC_1: Portal registration and Login of different users on the portal and role based access to issue, attest, claim, verify and view credentials | As a candidate user, I should be able to view my Landing Page so that I can access features of the application. | NA | NA | 1 | NA | We have been requested to put a hold on FE
10 | UC_2: A type of E Credential is issued as per its process | As an admin user, I should be able to pull student information from CASA, select a template so that I can issue credentials to the students. | 43 | 12 | 0 | 55
11 | UC_4: Candidate is able to obtain verifiable credentials through Learner Wallet | As a candidate, I should be able to view the credentials issued to me so that I can download and share. | 30 | 8 | 0 | 38 | 1. Estimates for share is not included. 2. Estimates for incorporating "verified by UPSMF" logo is not included.
12 | UC_2: A type of E Credential is issued as per its process | As an admin, I want system to generate marksheet automatically and share it with students for any exam results uploaded on registry. | 43 | 12 | 0 | 55 | 1. csv file template.
13 | UC_4: Candidate is able to obtain verifiable credentials through Learner Wallet | As a candidate, I should be able to view the credentials issued to me so that I can download and share. | 30 | 8 | 0 | 38
14 | UC_3: The admin/ workplace is able to attest claim requests of candidates | As an admin, I should be able to attest student's claim for registration certificate so that system can generate the registration certificate. | 73 | 24 | 0 | 97 | 1. Assuming we will be informed of any upload. 2. Assuming we will get information to identify new uploads in CASA DB.
15 | UC_5: Candidate is able to submit claims for registration/work experience/marksheet for attestation by issuer through Digilocker | As a candidate, I should be able to claim for a registration certificate so that same can be issued to me. | 20 | 8 | 0 | 28
16 | UC_4: Candidate is able to obtain verifiable credentials through Learner Wallet | As a candidate, I should be able to view the credentials issued to me so that I can download and share. | 30 | 8 | 0 | 38
17 | UC_2: A type of E Credential is issued as per its process | As an admin, I should be able to issue certificate to candidates for PIAA assessments submitted by PIAA Nodal. | 20 | 8 | 0 | 28
18 | UC_4: Candidate is able to obtain verifiable credentials through Learner Wallet | As a candidate, I should be able to view the credentials issued to me so that I can download and share. | 30 | 8 | 0 | 38
19 | UC_2: A type of E Credential is issued as per its process | As a workplace user, I should be able to issue work experience certificate to candidate by entering the required details. | 15 | 4 | 0 | 19
20 | UC_4: Candidate is able to obtain verifiable credentials through Learner Wallet | As a candidate, I should be able to view the credentials issued to me so that I can download and share. | 30 | 8 | 0 | 38
21 | UC_3: The admin/ workplace is able to attest claim requests of candidates | As a work place user I should be able to attest candidate's claim for work experience certificate. | 25 | 8 | 0 | 33 | We need what attributes constitutes the workplace so that we can generate the schema.
22 | UC_4: Candidate is able to obtain verifiable credentials through Learner Wallet | As a candidate user, I should be able to access my credentials in Learner Wallet. | 35 | 8 | 0 | 43
23 | UC_5: Candidate is able to submit claims for registration/work experience/marksheet for attestation by issuer through Digilocker | As a candidate user, I should be able to claim credentials from Learner Wallet. | 15 | 4 | 0 | 19
24 | UC_6: Candidate is able to obtain and share credentials in e-resume format through Digilocker | As a candidate user, I should be able to access and share eResume from Learner Wallet. | 10 | 4 | 0 | 14
25 | UC_7: Verify credentials of candidates by scanning embedded QR Code/clicking on embedded link | As a verifier user, I should be able to verify a credential by scanning QR code. | 10 | 4 | 0 | 14
26 | UC_8: The Admin is able to define credential schema through backend and frontend UI | As an admin user, I should be able to create scheme for a credential. | NA | NA | 1 | NA | need more clarification
27 | UC_9: E-cred module data emitted for insights generation (This needs to be culled out further) | As an admin user, I should be able to access dashboard to gain insights. | NA | NA | 1 | NA | how do we fetch drop-out rates in institutes, unemployment rate among registered candidates
Total |  |  | 534 | 160 |  | 694 | 9
|  |  | 66.75 | 20 |  | 86.75

## New E-creds Estimates
S. No. | Macro Use Case | Desc | eCreds User Story | BE | Testing | If NA | Total | Status
1 | UC_1: Portal registration and Login of different users on the claims portal and role based access to issue, attest, view and claim credentials |  |  | 25 |  |  | 25
register user
user login with otp
2 | UC_2: A type of E Credential is issued by the admin and can be viewed by the candidate (claim-issue-view process) | Re-verification for data source, For the data we need to fetch from Casa |  |  |  |  | 12 hrs / Credentials
3 | UC_3 : Candidate is able to obtain verifiable credentials through Digilocker | Digilocker - key needed as published |  | 80 |  |  | 80
4 | UC_4: Candidate is able to submit edit claims for credentials |  |  | 80 |  |  | 40
5 | UC_5: Candidate is able to create, view, and share ‘Competency Passbook’ | View and Share, create need to reconsider |  | 40 |  |  | 120
6 | UC_6: Candidate is able to create, view, and share ‘Verifiable resume’ | API to extend for reference implementation? |  | 120 |  |  | 120
7 | UC_7: Verify credentials of candidates by scanning embedded QR Code/clicking on embedded link | API implemented, should be exposed on domain |  | 120 |  |  | 15
8 | UC_8: The Admin is able to define credential schema through backend and frontend UI | Already in place, But it’s a developer involvement needed. Need more descripption. |  | 15 |  |  | 10
9 | UC_9: E-cred module data emitted for insights generation (This needs to be culled out further) | clarification needed |  | 50
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Total | [7 empty] | 9

## Affiliation Estimates
S.No | Macro Use Case | Affiliation Use Case | UX | FE | BE | QA | If NA | Total | Comments
1 | UC_1: User Management | Add Single User |  | 10 | 10 | 6 | 0 | 26
2 | UC_1: User Management | Add Bulk Users |  | 25 | 25 | 15 | 0 | 65
3 | UC_1: User Management | Delete Single / Multiple Users |  | 15 | 10 | 7.5 | 0 | 32.5
4 | UC_1: User Management | Edit Single User |  | 10 | 10 | 6 | 0 | 26
5 | UC_2: Creation & Publication of forms by Admin | Deletion of Draft forms |  | 10 | 10 | 6 | 0 | 26
6 | UC_2: Creation & Publication of forms by Admin | Extracting forms |  | 10 | 10 | 6 | 0 | 26 | MVP to be Download XML instead of CSV
7 | UC_3: Filling of application by applicant | Choose type of application | UX Needed | 16 | 16 | 10 | 0 | 42
8 | UC_3: Filling of application by applicant | Re-submission of application [POC] |  | 20 | 5 | 7.5 | 0 | 32.5
9 | UC_4: Desktop assessment of the applications by assessors | Viewing resubmitted application |  | 5 | 5 | 3 | 0 | 13
10 | UC_5: Submission of assessment fee by applicant | Submission of assessment fee by applicant |  | NA | NA | NA | 1 | 0 | Raj to get back with more Clarity
11 | UC_6: Creation & viewing of assessment schedules by admin | Creation of assessment schedule (bulk upload method) | UX Needed | 25 | 25 | 15 | 0 | 65
12 | UC_6: Creation & viewing of assessment schedules by admin | Admin: Viewing assessment schedule | UX Needed | 25 | 25 | 15 | 0 | 65
13 | UC_9: Issuance of documents by government | Issuance of documents by government |  | NA | NA | NA | 1 | 0 | Raj to get back with more Clarity
14 | UC_10: Viewing results | Viewing comments |  | 40 | 8 | 15 | 0 | 63
15 | UC_10: Viewing results | Viewing documents | UX Needed | NA | NA | NA | 1 | 0 | Raj to get back with more Clarity
16 | UC_11: Notifications | In App Notifications [Additional Tab] |  | 30 | 40 | 21 | 0 | 91
17 | UC_11: Notifications | email Notifications |  | 0 | 10 | 3 | 0 | 13
18 | UC_12: Certification Management | Certificate Management |  | NA | NA | NA | 1 | 0 | Raj to get back with more Clarity
19 | UC_1: User Management | OTP based login by on ground assessors |  | 15 | 0 | 4.5 | 0 | 19.5
20 | UC_2: Creation & Publication of forms by Admin | Previewing & publishing forms | UX Needed | NA | NA | NA | 1 | 0 | Raj to get back with more Clarity
21 | UC_3: Filling of application by applicant | Application navigation |  | NA | NA | NA | 1 | 0 | Enketo does not have this feature. Cannot be implemented with Enketo
22 | UC_3: Filling of application by applicant | Save as draft |  | 15 | 10 | 7.5 | 0 | 32.5
23 | UC_3: Filling of application by applicant | Submitting the Application |  | 10 | 10 | 6 | 0 | 26
24 | UC_4: Desktop assessment of the applications by assessors | Verification of application | UX Needed | 32 | 42 | 20 | 0 | 94
25 | UC_6: Creation & viewing of assessment schedules by admin | Creation of assessment schedule (one at a time) |  | 45 | 30 | 22.5 | 0 | 97.5
26 | UC_7: Conduction of on-ground assessments by assessors | Assessor: View assessment schedule |  | 25 | 25 | 15 | 0 | 65
27 | UC_7: Conduction of on-ground assessments by assessors | Preview PDF download [OGA] |  | 40 | 30 | 21 | 0 | 91
Total (in hours) |  |  |  | 423 | 356 | 232.5 |  | 1011.5
Total (in days) |  |  |  | 52.875 | 44.5 | 29.0625 |  | 126.4375

## Exams Estimates
REQUIREMENT | [11 empty] | STATUS
S. No. | User | Epics | User story | Acceptance Criteria | Links | FE | BE | UX | Testing | If NA | Total | Sprint | Sprint Priority | Status | Remarks
1 | Admin | UC_1: User Management on Admin, Institute, Candidate, and Questions Setup Portal | As an admin, I am able to add users to the platform and assign them to their user roles so that they can perform the actions of their role (Admin, Institute, QR_C, QR_M, Candidate) |  |  | 19 | 15 |  | 10 | 0 | 44
2 | Admin | UC_1: User Management on Admin, Institute, Candidate, and Questions Setup Portal | As an admin, I am able to edit user information / role. |  |  | 19 | 15 |  | 10 | 0 | 44
3 | Admin | UC_1: User Management on Admin, Institute, Candidate, and Questions Setup Portal | As an admin, I am able to delete users after adding them |  |  | 19 | 15 |  | 10 | 0 | 44
4 | Institute | UC_1: User Management on Admin, Institute, Candidate, and Questions Setup Portal | As an institute, I am able to generate OTP on my email ID while logging in, so that I can successfully login and access the platform |  |  | 13 | 19 |  | 10 | 0 | 42 |  |  |  | Sendgrid sandbox, integration will be replace the prod version
5 | Candidate | UC_1: User Management on Admin, Institute, Candidate, and Questions Setup Portal | As a candidate, I am able to login to the candidate portal through email ID and password or OTP generated on my email. |  |  | 13 | 19 |  | 10 | 0 | 42
6 | QR_C | UC_1: User Management on Admin, Institute, Candidate, and Questions Setup Portal | As a QR_C, I am able to login to the Questions Setup portal through email ID and password or OTP generated on my email |  |  | 13 | 15 |  | 9 | 0 | 37
7 | All Users | UC_1: User Management on Admin, Institute, Candidate, and Questions Setup Portal | As a user, I am able to edit fields in ‘My Profile’ so that I can record any changes in my profile |  |  | 19 | 19 |  | 10 | 0 | 48
8 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to view a candidate management tab. Further Detailing: - Admin logs into the admin portal - Admin lands on the home page with following options a. Affiliation b. Ecred issuance c. Candidate Management d. Ratings e. Exam Management f. Assessment Management - Admin clicks on the Candidate Management option |  |  | 23 |  |  | 10 | 0 | 33
9 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to upload a list of candidates admitted to every institute received from Admissions portal |  |  | 12 | 12 |  | 8 | 0 | 32
10 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to view a exam management tab on the admin portal |  |  | 8 | 0 |  | 4 | 0 | 12
11 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to add exam cycles for institutes to register/onboard to with the following information Exam Cycle fields: Exam cycle name, course name, start date, end date <fields to be updated> |  |  | 19 | 13 |  | 10 | 0 | 42
12 | Admin | UC_2: Exam Management as an admin | As an admin, I am able delete exam cycles |  |  | 13 | 12 |  | 8 | 0 | 33
13 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to add exams in every exam cycle. Exam fields: Exam subject name, date, time, max marks <fields to be updated> |  |  | 19 | 23 |  | 13 | 0 | 55 |  |  |  | is this scheduling ? If yes consider the estimation. Need clarity. Save complete data on Postgres and metadata on ES. Think of caching startegy
14 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to delete exams in every exam cycle. Exam fields: Exam subject name, date, time, max marks <fields to be updated> |  |  | 13 | 23 |  | 10 | 0 | 46 |  |  |  | when scheduled and the exam appears adhoc ?
15 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to download a csv template for bulk creation of exam cycles and exams |  |  | 8 | 23 |  | 10 | 0 | 41
16 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to upload a csv for bulk creation of exam cycles and exams |  |  | 13 | 30 |  | 12 | 0 | 55
17 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to view list of exam cycles |  |  | 13 | 19 |  | 10 | 0 | 42
18 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to view list of exams |  |  | 13 | 19 |  | 10 | 0 | 42
19 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to view pre-created exam cycles for every course |  |  | 19 | 0 |  | 8 | 0 | 27
20 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to see the list of institutes that have made payment for an exam cycle |  |  | 19 | 24 |  | 12 | 0 | 55
21 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to see the list of candidates for which the institutes have made the payment |  |  | 19 | 24 |  | 12 | 0 | 55
22 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to update the CCTV verification status of institutes for an exam cycle |  |  | 12 | 12 |  | 8 | 0 | 32
23 | Admin | UC_2: Exam Management as an admin | As an admin, I am able to upload question paper PDFs for every exam |  |  | 19 | 13 |  | 10 | 0 | 42 |  |  |  | what should I do with uploaded PDF ? Where to upload PDF? Cloud or DB ?
24 | Institute | UC_3: Exam Management as an Institute | As an institute, I am able to register for an exam cycle |  |  | 20 | 20 |  | 12 | 0 | 52 |  |  |  | Need clarity and design !!!
25 | Institute | UC_3: Exam Management as an Institute | As an institute, I am able to view the list of candidates in the institute in different courses |  |  | 19 | 35 |  | 16 | 0 | 70
26 | Institute | UC_3: Exam Management as an Institute(V1) | As an institute, I am able to download the list of candidates in different courses. |  |  | 12 | 15 |  | 8 | 0 | 35
27 | Institute | UC_3: Exam Management as an Institute(V1) | As an institute, I am able to upload a list of candidates as a csv appearing for an exam cycle (including list of subjects they are appearing for). |  |  | 19 | 30 |  | 15 | 0 | 64
28 | Institute | UC_3: Exam Management as an Institute(V1) | As an institute, I am able to view the payment amount for the uploaded list of students. |  |  | 20 | 20 |  | 12 | 0 | 52
29 | Institute | UC_3: Exam Management as an Institute(V1) | As an institute, I am able to pay exam fees for the list of candidates that was uploaded before making the payment. |  |  |  | 80 |  | 30 | 0 | 110 |  |  | add tentative for unknowns in payment | 1. Integrate with payment gateway 2. Payment success and store info 3. Payment failure and store info 4. payment was successful bt transaction response failed 5. payment failure and response not recived 6. Refund usecase ? 7. redirect to payment gateway site and then get the response and again redirect to our page
30 | Institute | UC_3: Exam Management as an Institute(V1) | As an institute, I am able to view list of students for whom the payment has been made successfully. |  |  | 20 | 20 |  | 12 | 0 | 52
31 | Institute | UC_3: Exam Management as an Institute(V1) | As an institute, I am able to repeat the process to make repeat payments. <Payment vendor to be updated> <Schema for exam fees to be updated> | [6 empty] | 0
32 | Institute | UC_3: Exam Management as an Institute(V2) | As an institute, I am able to filter the list of candidates in different courses on the portal. | [6 empty] | 0 |  |  |  |  | for all V2 we need clarity
33 | Institute | UC_3: Exam Management as an Institute(V2) | As an institute, I am able to submit the filtered list of candidates. | [6 empty] | 0 |  |  |  |  | need clarification. What is meant by submit
34 | Institute | UC_3: Exam Management as an Institute(V2) | As an institute, I am able to upload a csv of candidates (including of subjects they are appearing for). | [6 empty] | 0 |  |  |  |  | need template for csv. Wherever there is download and upload csv
35 | Institute | UC_3: Exam Management as an Institute(V2) | As an institute, I am able to view the payment amount for the list of candidates. | [6 empty] | 0
36 | Institute | UC_3: Exam Management as an Institute(V2) | As an institute, I am able to pay exam fees for the list of the candidates filtered. | [6 empty] | 0
37 | Institute | UC_3: Exam Management as an Institute(V2) | As an institute, I am able to repeat the process to make repeat payments. <Payment vendor to be updated> <Schema for exam fees to be updated> | [6 empty] | 0
38 | Institute | UC_3: Exam Management as an Institute | As an institute, I am able to view the status of CCTV verification of my institute |  |  | 8 | 8 |  | 4 | 0 | 20
39 | Institute | UC_3: Exam Management as an Institute | As an institute, I am able to download the question paper PDF for an exam 30 minutes before the scheduled exam time |  |  | 4 | 20 |  | 8 | 0 | 32 |  |  |  | front end should have a button that will be enabled only 30 min before the exam. Once enabled then fetch the url. Also time should be fetched from server and not client since the time can be changed on client system
40 | Candidate | UC_4: Hall Ticket Management | As a candidate, I am able to view/download candidate hall ticket on the candidate portal by giving my “Exam Registration number” and “Date of Birth” Note: Hall ticket is generated based on mapping between candidates (payment for whom is made by institutes) and exam centres (institutes which have cctv verification done) <business logic to be updated> |  |  | 20 | 45 |  | 20 | 0 | 85 |  |  |  | assuming can be downloaded only after the exam is scheduled and published when and who will generate the exam registartion number
41 | Candidate | UC_4: Hall Ticket Management | As a candidate, I am able to request data correction in hall ticket |  |  | 13 | 13 |  | 8 | 0 | 34
42 | Admin | UC_4: Hall Ticket Management | As an admin, I am able to view requests for candidate data correction |  |  | 13 | 13 |  | 8 | 0 | 34
43 | Admin | UC_4: Hall Ticket Management | As an admin, I am able to approve/reject requests for candidate data correction |  |  | 13 | 13 |  | 8 | 0 | 34
44 | Institute | UC_4: Hall Ticket Management | As an institute, I am able to update candidate data |  |  | 13 | 13 |  | 8 | 0 | 34
45 | System | UC_5: Question Paper Setup on Question Setup Portal | Prashna Bhandar (CoKreat instance for UP SMF) should be used for the Question Setup Portal fulfilling the below use cases. Admin should be able to login to Prashna Bhandar and all required security criteria should be met. | [6 empty] | 0 |  |  |  |  | all required security criteria should be met. - meaning
46 | QR_C | UC_5: Question Paper Setup on Question Setup Portal | As a QR_C, I am able to upload questions for every course. | [6 empty] | 0
46 | QR_C | UC_5: Question Paper Setup on Question Setup Portal | As a QR_M, I am able to review questions submitted by QR_C. | [6 empty] | 0
47 | QR_C | UC_5: Question Paper Setup on Question Setup Portal | As a QR_C, I am able to download a csv template to upload questions. Question fields: Question, Course, Subject, Difficulty | [6 empty] | 0
47 | QR_C | UC_5: Question Paper Setup on Question Setup Portal | As a QR_C, I am able to upload a csv with multiple questions Question fields: Question, Course, Subject, Difficulty | [6 empty] | 0
48 | Exam Controller | UC_5: Question Paper Setup on Question Setup Portal | As an exam controller, I am able to set a blueprint for a question paper | [6 empty] | 0
49 | Admin | UC_5: Question Paper Setup on Question Setup Portal | As an admin, I am able to generate question papers based on the blueprint | [6 empty] | 0
50 | Admin | UC_5: Question Paper Setup on Question Setup Portal | As an admin, I should be able to re-generate different random question papers everytime I click on the “Generate Question Paper” button based on the blueprint | [6 empty] | 0
51 | Admin | UC_5: Question Paper Setup on Question Setup Portal | As an admin, I am able to download a question paper for any course | [6 empty] | 0
52 | Admin | UC_5: Question Paper Setup on Question Setup Portal | As an admin, I should have an offline documentation for using the questions setup portal to be shared with the QR_C, QR_M and exam controller | [6 empty] | 0
53 | Institute | UC_6: Exam Result Generation | As an institute, I am able to update status of dispatch and upload proof of dispatch for an exam in an exam cycle |  |  | 16 | 18 |  | 11 | 0 | 45 |  |  |  | Third party Exam portal ?
54 | Institute | UC_6: Exam Result Generation | As an institute, I am able to enter internal (theory+practical) marks for every candidate for every course through a CSV upload <schema to be updated> |  |  | 12 | 40 |  | 15 | 0 | 67 |  |  |  | Third party Exam portal ?
55 | Admin | UC_6: Exam Result Generation | As an admin, I am able to view dispatch status and proof of dispatch for every institute for every exam in every exam cycle |  |  | 16 | 18 |  | 11 | 0 | 45 |  |  |  | Third party Exam portal ?
56 | Admin | UC_6: Exam Result Generation | As an admin, I am able to view/export internal marks of every candidate for every exam in every exam cycle |  |  | 16 | 30 |  | 14 | 0 | 60 |  |  |  | Third party Exam portal ?
57 | Admin | UC_6: Exam Result Generation | As an admin, I am able to upload final marks for every candidate in every course in every exam cycle <schema to be updated> |  |  | 20 | 20 |  | 12 | 0 | 52
58 | Admin | UC_6: Exam Result Generation | As an admin, I am able to generate results for every exam in every exam cycle |  |  | 12 | 35 |  | 14 | 0 | 61
59 | Admin | UC_6: Exam Result Generation | As an admin, I am able to view marks for an exam cycle for every candidate |  |  | 23 | 25 |  | 14 | 0 | 62
60 | Admin | UC_6: Exam Result Generation | As an admin, I am able to publish results for an exam cycle after all results have been generated |  |  | 13 | 13 |  | 8 | 0 | 34
61 | Candidate | UC_6: Exam Result Generation | As a candidate, I am able to view final result card by giving my “Exam Registration number” and “Date of birth” |  |  | 20 | 20 |  | 12 | 0 | 52
61 | Candidate | UC_6: Exam Result Generation | As a candidate, I am able to download final result card by giving my “Exam Registration number” and “Date of birth” |  |  | 12 | 20 |  | 9 | 0 | 41
62 | Candidate | UC_6: Exam Result Generation | As a candidate, I am able to initiate a re-totalling request for selected subjects |  |  | NA | NA |  | NA | 1 | NA |  |  |  | Third party Exam portal ?
63 | Admin | UC_6: Exam Result Generation | As an admin, I am able to view the re-totalling requests in an exam cycle |  |  | NA | NA |  | NA | 1 | NA |  |  |  | Third party Exam portal ?
64 | Admin | UC_6: Exam Result Generation | As an admin, I am able to update marks of the candidates for every exam in an exam cycle | [6 empty] | 0 |  |  |  |  | need clarity on the functional flow
65 | Admin | UC_6: Exam Result Generation | As an admin, I am able to see a dashboard of the marks of all candidates for an exam cycle using metabase <details on types of views in dashboard to be updated> | [6 empty] | 0 |  |  |  |  | <details on types of views in dashboard to be updated> effort will be based on this.
|  |  |  | Total (in hours) |  | 711 | 948 |  | 513 |  | 2172
|  |  |  | Total (in days) |  | 88.875 | 118.5 |  | 64.125 |  | 271.5

## Assessments Bugs
Summary | Issue key | Status | Priority | Reporter | Category | QA Comments | BE Efforts (in hours) | FE Efforts (in hours) | DEV Comments
Search Candidate ¦¦ Search results are irrelevant to the search parameter in admin login | UPHRH-4664 | READY | High | Dharani Vamanamurthy | Code |  |  |  | Discussion needed with Maney for search indexer
Assessment/Question Set Creation ¦¦ When creator click on save as draft button in assessment/Question Set page it is directing to draft page in workspace | UPHRH-4624 | READY | High | Dharani Vamanamurthy | Code |  |  | 8
Global Search ¦¦ When the user clicks on global search, The Compentency Level field from the FRACCL filters is missing | UPHRH-4416 | READY | High | Singuru Jyostna Rani | Code |  |  |  | Feature not available in Sunbird It will require code change.
All my contents ¦¦ When user try to filter with function and role, filter results has only self and piaa question set(Assessment and Course are missing) | UPHRH-4244 | DEV IN-PROGRESS | High | Dharani Vamanamurthy | Code |  | 6
Search Candidate ¦¦ Search results are irrelevant to the search parameter in nodal login | UPHRH-3796 | READY | High | Dharani Vamanamurthy | Code+ Configuration |  |  |  | Discussion needed with Maney for search indexer
Download Certificate ¦¦ Certificate is not available for the completed Assessment/Course | UPHRH-3341 | DEV IN-PROGRESS | Highest | Dharani Vamanamurthy | Code+ Configuration +GCP Cloud |  | 12
Sort functionality not working as per the selection in work space all my contents | UPHRH-3159 | DEV IN-PROGRESS | High | Singuru Jyostna Rani | Code |  |  |  | Required code change since sunbird functionality not supporting
View Course Dashboard ¦¦ Throwing 500 error when user select the batch (creater facing this when batch is created to the assessment and when he tries to open that assessemnt and clicks on view course dashboard) | UPHRH-2918 | DEV IN-PROGRESS | High | Dharani Vamanamurthy | Code+ Configuration |  |  |  | For this issue some “druid” server is not up
"DIKSHA" should be removed from Email Body when OTP is received | UPHRH-2640 | READY | Highest | Singuru Jyostna Rani | Code + Configuraion |  | 4 |  | Updated email template should get it from UPTSU
Logout ¦¦ When an user logout and login, not showing any options under Profile icon intermittently | UPHRH-2639 | READY | High | Singuru Jyostna Rani | Code | QA needs to Monitor. Unable to reproduce now
Registration ¦¦ Password criteria notification should not show when Password matches | UPHRH-2633 | READY | High | Singuru Jyostna Rani | Code |  |  | 6
User Registration ¦¦ 404 Error throwing when user click on continue after confirm password | UPHRH-2562 | READY | High | Dharani Vamanamurthy | Code |  | 8
In upload content ¦¦ file is getting uploaded before click on upload button | UPHRH-2424 | READY | High | Dharani Vamanamurthy | Code |  |  |  | Existing sunbird functionality. Code change is required to fix this.
Getting BGMS status when question is selected from question set and course unit is selected form course | UPHRH-2342 | DEV IN-PROGRESS | High | Singuru Jyostna Rani | Configuration |  |  | 6
Registration ¦¦ OTP is not received on yopmail . ( received from shishir.suman@tarento.com ) | UPHRH-2237 | DEV IN-PROGRESS | Highest | Singuru Jyostna Rani | Code |  | 4
All my contents ¦¦ Filters not working based on FRACCL | UPHRH-2232 | READY | High | Dharani Vamanamurthy | Code |  | 4 | 1
Designation is not being updated while creating template for certificate | UPHRH-2176 | READY | High | Singuru Jyostna Rani | Code + Configuraion |  | 4 | 4
Add from Library ¦¦ BGMS label is displaying in library while uploading content | UPHRH-1634 | DEV IN-PROGRESS | High | Salman Shariq | Code (Requirement Change) |  |  | 6
Batch Creation ¦¦ User could not see terms & condition page after clicking “course Terms” Hyperlink. It was redirecting to home page | UPHRH-1609 | READY | High | Salman Shariq | Configuration |  |  | 4
Forget Password ¦¦ Throwing 500 error while resetting password in UAT for users | UPHRH-4720 | DEV IN-PROGRESS | Highest | Dharani Vamanamurthy | Code |  | 6
Creator Login - All my content ¦¦Throwing 412 Error when user try to open created question set as soon as it send for review | UPHRH-4722 | READY | High | Dharani Vamanamurthy | Code |  | 4 | 4
In admin login , Pending tab is showing all the students. it should show the list of students who have completed the assessment and nodal has send for evaluation. ( the candidate who are pending for evaluation should show) | UPHRH-4723 | READY | High | Singuru Jyostna Rani | Code |  |  |  | Discussion needed with Maney for search indexer
When admin selects issue certificate cta, then nodal feedback is not showing | UPHRH-4745 | DEV IN-PROGRESS | High | Singuru Jyostna Rani | Code |  | 1 | 4
CoKreat ¦¦ Throwing 404 error while creating Questionset in UAT | UPHRH-4780 | READY | Highest | Singuru Jyostna Rani | Invalid Defect |  |  | 8 | Maney - why marked it as invalid defect
When Admin Evaluate candidate with Not Issue Certificate, then the Nodal feedback column is appending with Admin comments | UPHRH - 5026 | READY | High | Singuru Jyostna Rani | Code |  |  | 4
Student is able to see the score while consuming when Blue Print question set is linked to Self assessment and self question set linked to self assessment (when selected summary type as duration) | UPHRH - 5337 | DEV IN-PROGRESS | High | Singuru Jyostna Rani |  |  |  | 16
When the questions are created from coKreat then it is not showing in Sunbird-ED Library (Data is not syncing between Sunbird Ed & CoKreat) | UPHRH - 5279 | DEV IN-PROGRESS | Highest | Singuru Jyostna Rani |  |  | 16 |  | Dependency on 4780