## Sheet1
S. No. | User | Epics | Feature | Sub-feature | User story | Acceptance Criteria | Comment | request body | response | available functionality in sunbird-rc | Questions | Change scope | Links | Tech | FE | BE | UX | Testing | Total | Sprint | Sprint Priority | Status | Remarks
1 | Candidate | Learner Wallet | View credentials | 1. View list of added credentials 2. Sort 3. Filter | As a candidate, I should be able to view list of credentials issued to me so that I can use them as per my need. | 1. User should be able to view list of credentials issued to him/her. 2. User should be able to sort the list basis the date of issue. 3. User should be able to filter the list by Issuer Name. | /credentials/search | { "subject": { "id": "did:ulp:test" } } | [ { "id": "did:ulp:2e059022-a3a8-4c06-b06f-1aec1308649b", "type": [ "VerifiableCredential", "UniversityDegreeCredential" ], "issuer": "did:ulp:9d46124a-201a-4ff8-8bd4-1f25ce985bfa", "@context": [ "https://www.w3.org/2018/credentials/v1", "https://www.w3.org/2018/credentials/examples/v1" ], "issuanceDate": "2023-02-06T11:56:27.259Z", "expirationDate": "2023-02-08T11:56:27.259Z", "credentialSubject": { "id": "did:ulp:test", "grade": "9.23", "programme": "B.Tech", "certifyingInstitute": "IIIT Sonepat", "evaluatingInstitute": "NIT Kurukshetra" } }, { "id": "did:ulp:85ef0606-daf4-4e84-b244-a7b5a646918d", "type": [ "VerifiableCredential", "UniversityDegreeCredential" ], "issuer": "did:ulp:9d46124a-201a-4ff8-8bd4-1f25ce985bfa", "@context": [ "https://www.w3.org/2018/credentials/v1", "https://www.w3.org/2018/credentials/examples/v1" ], "issuanceDate": "2023-02-06T11:56:27.259Z", "expirationDate": "2023-02-08T11:56:27.259Z", "credentialSubject": { "id": "did:ulp:test", "grade": "9.23", "programme": "B.Tech", "certifyingInstitute": "IIIT Sonepat", "evaluatingInstitute": "NIT Kurukshetra" } }, { "id": "did:ulp:05974eb3-07f6-40c2-9b2b-761350214497", "type": [ "VerifiableCredential", "UniversityDegreeCredential" ], "issuer": "did:ulp:9d46124a-201a-4ff8-8bd4-1f25ce985bfa", "@context": [ "https://www.w3.org/2018/credentials/v1", "https://www.w3.org/2018/credentials/examples/v1" ], "issuanceDate": "2023-02-06T11:56:27.259Z", "expirationDate": "2023-02-08T11:56:27.259Z", "credentialSubject": { "id": "did:ulp:test", "grade": "9.23", "programme": "B.Tech", "certifyingInstitute": "IIIT Sonepat", "evaluatingInstitute": "NIT Kurukshetra" } }, { "id": "did:ulp:c7578f40-f400-4db8-94fb-556b2bdb5763", "type": [ "VerifiableCredential", "UniversityDegreeCredential" ], "issuer": "did:ulp:9d46124a-201a-4ff8-8bd4-1f25ce985bfa", "@context": [ "https://www.w3.org/2018/credentials/v1", "https://www.w3.org/2018/credentials/examples/v1" ], "issuanceDate": "2023-02-06T11:56:27.259Z", "expirationDate": "2023-02-08T11:56:27.259Z", "credentialSubject": { "id": "did:ulp:test", "name": "John DOe", "grade": "9.23", "programme": "B.Tech", "certifyingInstitute": "IIIT Sonepat", "evaluatingInstitute": "NIT Kurukshetra" } }, { "id": "did:ulp:08cdceac-51aa-4291-a4a4-421782189043", "type": [ "VerifiableCredential", "UniversityDegreeCredential" ], "issuer": "did:ulp:9d46124a-201a-4ff8-8bd4-1f25ce985bfa", "@context": [ "https://www.w3.org/2018/credentials/v1", "https://www.w3.org/2018/credentials/examples/v1" ], "issuanceDate": "2023-02-06T11:56:27.259Z", "expirationDate": "2023-02-08T11:56:27.259Z", "credentialSubject": { "id": "did:ulp:test", "name": "John DOe", "grade": "9.23", "programme": "B.Tech", "certifyingInstitute": "IIIT Sonepat", "evaluatingInstitute": "NIT Kurukshetra" } } ] |  | API - List credentials - Sort/search/filter by Issuer | ULP or others | https://github.com/Unified-Learner-Passbook | node js / ts
2 | Candidate | Learner Wallet | View credentials | 4. eResume mode | As a candidate, I should be able to view my credentials in eResume mode so that I can know how it will look to others. | 1. User should be able to switch the view from list mode to eResume mode and vice versa. 2. All user types will have a common view in eResume mode. 3. The most common and widely used features should be incorporated in design. | not able to verify the functionality because UI not available |  |  |  | Whats is eResume mode? Definition of most common and widely? Required api will be identified and Implemented. | ULP
3 | Candidate | Learner Wallet | Download | 1. Download credentials 2. Download eResume | As a candidate, I should be able to download my credentials so that I can view and share them outside the application. | 1. User should be able to select one, many or all the issued credentials to download. 2. User should be able to select the destination folder for downloading. 3. Success or error message should be displayed post completion of download process. 4. User should be able to download all the credentials in eResume mode (single file). | CertificateAPI - /api/v1/{entityname}/{idx} Note - DB of both RC and new apis in synch. > Not able to verify the functionality from UI, render credentials available. |  |  |  | Dowload as RAW or PDF Reference - getCertificatePDF. Work flow API to get all credential in single file. - Node js change. | ULP
4 | Candidate | credential Issuance | Request Issuance | 1. Request issuance of a credential | As a candidate, I should be able to request issuance of a credential which I am entitled to so that I can view it in my learner wallet. | 1. User should be able to select an Issuing Entity. 2. User should be able to view and fill required information for the credential issuance (this will vary from one Issuing Entity to another Issuing Entity). 3. User should be able to submit the request. 4. User should be able to track the status post submission. | issue credentials functionality available 1. /credentials/issue | { "credential": { "@context": [ "https://www.w3.org/2018/credentials/v1", "https://www.w3.org/2018/credentials/examples/v1" ], "id": "did:ulp:b4a191af-d86e-453c-9d0e-dd4771067235", "type": [ "VerifiableCredential", "UniversityDegreeCredential" ], "issuer": "did:ulp:9d46124a-201a-4ff8-8bd4-1f25ce985bfa", "issuanceDate": "2023-02-06T11:56:27.259Z", "expirationDate": "2023-02-08T11:56:27.259Z", "credentialSubject": { "id": "did:ulp:b4a191af-d86e-453c-9d0e-dd4771067235", "grade": "9.23", "programme": "B.Tech", "certifyingInstitute": "IIIT Sonepat", "evaluatingInstitute": "NIT Kurukshetra" }, "options": { "created": "2020-04-02T18:48:36Z", "credentialStatus": { "type": "RevocationList2020Status" } } }, "credentialSchemaId": "clfc6gg3t0004tj14ttxn4hbn", "tags": ["tag1", "tag2", "tag3"] } |  |  | Who will be the Issuence Entity ? Whare will find and need api to find issueing entity. - > IssueCertificateAPI ? - need Api to issue certificate Track the status of Request - API to get the status of requiest and what are the state of certificate request status.
5 | Candidate | credential Verification | Share credentials | 1. Share issued credential(s) | As a candidate, I should be able to share one, many or all my issued credentials so that others (inside or outside the platform) can ascertain my capabilities. | 1. User should be able to select one, many or all the issued credentials to share. 2. User should be able to select authorized verifier(s) from dropdown or enter valid email ID(s) to share. 3. Success or error message should be displayed post completion of sharing process. | Not able to find way to share the credentials. |  |  |  | List of authorised verifier?
6 | Candidate | credential Verification | Share eResume | 1. Share eResume | As a candidate, I should be able to share my eResume so that other can ascertain my capabilities. | 1. User should be able to preview e-Resume before sharing. 2. User should be able to select authorized verifier(s) from dropdown or enter email ID(s) to share. 3. Success or error message should be displayed post completion of sharing process. | eResume not needed in the current delivery
7 | Credential Issuer | credential Issuance | Issue credential | 1. Add a new credential to a candidate's learner wallet | As a credential issuer, I should be able to issue credential to a candidate so that same should gets added in his/her wallet. | 1. User should be able to select a credential and then candidate(s) to issue credential. 2. Success or error message should be displayed post completion of issuance process. 3. Credentials should get added in candidate(s) learner wallet after successful issuance. | /credentials/issue |  |  |  | 1. Need to build a wallet or have to use third-party wallet. 2.
8 | Credential Issuer | credential Issuance | View credential Issuance Request | 1. View list of credential issuance request 2. Sort 3. Filter | As a credential issuer, I want all the pending and completed credential issuance requests arranged in a list so that it is easy for me to work on. | 1. User should be able to view sperate list for pending and completed requests. 2. User should be able to sort the list basis the date to prioritize. 3. User should be able to filter by Candidate Name, Credentials Name. | need to verify on UI. My understanding - credentials created by candidate, will be displayed on UI with the help of search. - verify credentials endpoint will be called. Can be executed for one user at a time. | /credentials/did:ulp:13284f2c-35ce-419c-98c4-95ce19485c96/verify | { "status": "ISSUED", "checks": [ { "active": "OK", "revoked": "OK", "expired": "NOK", "proof": "OK" } ] } |  | 1.Refer to the status check functionality
9 | Credential Issuer | credential Issuance | Approve or Reject credential Issuance Request | 1. Verify a credential issuance request 2. Approve a credential issuance request 3. Reject a credential issuance request | As a credential issuer, I should be able to approve credential issuance request of a candidate so that same should gets added in his/her wallet. | 1. User should be able to select a request from the pending list. 2. User should be able to view information submitted in a request. 3. User should be able to either approve or reject a request. 4. Candidate should be notified after user takes any action. 5. If user approves a request, credential should get added to the candidate's learner wallet. | need to verify on UI. Approve or reject available in sunbird rc claim approval service. But how this can be integrated between new endpoint and rc claim. Verify and approve is same or different. Reject is not available in new endpoint. |  |  |  | 2
10 | Admin | User Management | Add User | 1. Add user to credential issuer role | As an admin, I should be able to create a new user under credential issuer role so that user can be onboarded. | 1. There should be an action button to add new user. 2. User should be able to fill in details for a new user. 3. The fields for new user creation are - User ID, First Name, Last Name, Role, email ID and Mobile Number. All fields are mandatory to fill. 4. All fields are mandatory to fill. System should show an error message if any field is left blank. 5. All fields will have some format constraints. System should show an error message if there is any non compliance. 6. If a new user is created successfully, system should show a new user creation message. | /api/user/v1/create /api/user/v1/role/assign
11 | Admin | User Management | Manage User | 1. Activate user 2. Deactivate user | As an admin, I should be able to activate or deactivate existing users so that I can control their access to the application. | 1. All the existing users should be shown in the list. 2. If the list gets large, page-wise or scroll down view should be incorporated. 3. The list should have columns for - User ID, Name, Role, email ID, Mobile Number and Status (Active or Inactive). 4. Rows of the list should have a switch button for activating and deactivating. 5. User should be able to set the switch to either activate or deactivate. 6. User access should be determined from the status of the switch. | /api/user/v1/block /api/user/v1/unblock |  |  | Revoke credentials schema?? -
12 | Admin | Dashboard | View Dashboard | 1. Insights on pending credential issuance requests 2. Insights on new user onboarding/adoption 3. Insights on usage pattern
13 | Admin | Schemas | Create Schemas | 1. Create schemas for Credentials 2. Create schemas for eResume | As an admin, I should be able to create schemas for credentials and eResume. | 1. There should be an action button to start the process of creating a new schema. 2. User should be able to select the entity which need the schema. | create schema available in new micreservice. /Schema | { "schema": { "@context": [ "https://www.w3.org/2018/credentials/v1", "https://www.w3.org/2018/credentials/examples/v1", "https://playground.chapi.io/examples/alumni/alumni-v1.json", "https://w3id.org/security/suites/ed25519-2020/v1" ], "type": "https://w3c-ccg.github.io/vc-json-schemas/", "version": "1.0", "id": "did:ulpschema:c9cc0f03-4f94-4f44-9bcd-b24a8696fa2", "name": "Proof of Academic Evaluation Credential", "author": "did:example:c276e12ec21ebfeb1f712ebc6f1", "authored": "2022-12-19T09:22:23.064Z", "schema": { "$id": "Proof-of-Academic-Evaluation-Credential-1.0", "$schema": "https://json-schema.org/draft/2019-09/schema", "description": "The holder has secured the <PERCENTAGE/GRADE> in <PROGRAMME> from <ABC_Institute>.", "type": "object", "properties": { "grade": { "type": "string", "description": "Grade (%age, GPA, etc.) secured by the holder." }, "programme": { "type": "string", "description": "Name of the programme pursed by the holder." }, "certifyingInstitute": { "type": "string", "description": "Name of the instute which certified the said grade in the said skill" }, "evaluatingInstitute": { "type": "string", "description": "Name of the institute which ran the programme and evaluated the holder." } }, "required": [ "grade", "programme", "certifyingInstitute", "evaluatingInstitute" ], "additionalProperties": false }, "proof": { "type": "object", "properties": { "created": "", "verificationMethod": "", "proofPurpose": "", "proofValue": "" }, "required": [] } }, "tags": [ "tag1", "tag2" ] } |  | ULP endpoint - /schema, create schema
14 | Verifier | credential Verification | View shared credentials | 1. View candidate wise list of shared credentials 2. View status - verified or not verified | As a verifier, I should be able to view list of shared credentials with status so that I can take appropriate actions. | 1. User should be able to view pending, verified and rejectd credentials in a sperate list. | /api/v1/verify in sunbird RC status is not available.
15 | Verifier | credential Verification | Verify shared credentials | 1. Verify a shared credential 2. Mark verified credentials as verified | As a verifier, I should be able to view a shared credential and verify its credibility so that I can know whether to accept or reject. | 1. User should be able to select a shared credentials and view its content. 2. User should be able to mark a credential as verified. | /api/v1/verify https://docs.sunbirdrc.dev/api-reference/other-apis/verify-api#usage |  |  | https://docs.sunbirdrc.dev/api-reference/other-apis/verify-api#usage https://docs.sunbirdrc.dev/learn/verifiable-credentials/what-issues-will-verifiable-credentials-address
https://docs.sunbirdrc.dev/learn/verifiable-credentials/what-are-the-key-roles-in-verifiable-credentials
Note on F1: ====== ID#AAAAr-1Kq_U Sagari Handa (2023-03-29 09:26:04) @mahesh.maney@tarento.com @deepanshu@samagragovernance.in please see color coding on what exists in ULP and can be leveraged as is (green), what will need some modifications (yellow) and what will need to be built (red) _Assigned to Mahesh Maney_ ------ ID#AAAAnqREZwg Deepanshu Singal (2023-03-30 08:49:45) @sagari@samagragovernance.in The user stories look fine to me. I have gone through the colour coding on it as well.
Note on F11: ====== ID#AAAAr-1Kq_I Sagari Handa (2023-03-29 09:23:47) In ULP - it follows a claim and attest model with issuer claiming and admin / dept confirming.
Note on F12: ====== ID#AAAAr-1Kq_M Sagari Handa (2023-03-29 09:24:30) Will be added in ULP in a later version. Can essentially be done by revoking access credential from an issuer.
Note on F14: ====== ID#AAAAr-1Kq_Q Sagari Handa (2023-03-29 09:24:43) from backend

## createfindSchema
| schema name | status
1 | Credentials | available on link provided, need to verify | https://github.com/Sunbird-RC/sunbird-rc-core/blob/main/api-documentation/schema-api.yaml
2 | eResume
3 | Candidate
4 | Issuer |  | https://github.com/Sunbird-RC/sunbird-rc-core/blob/main/api-documentation/issue-api.yaml
| type of credentials | VerifiableCredential
Courses Completed
titles of courses, and percentage of their completion
|  | certificate, degree/diploma certificate, competency based assessment certificates, skill assessment videos, additional certification | registeration certificate

## task
Create
view
share
verify

## Jira story
API - analysis and testing
1. Identity api - Analysis and testing
2. Credential MS - Analysis and testing
3. Credential Schema MS Analysis and testing

## Needed
API | List Credentials
Search/sort/filter by Issuer Name

## Questions
https://docs.sunbirdrc.dev/api-reference/other-apis/verify-api#usage | docs

## change-yellow
add user / manage users | which application have to change
where its available
How we can check existing functionality
Please clarify, whats available and not
Item no 8 | Its green means its available for user
So please share where this functionality is available.